## Slide 1: Decontamination of the SmartDet Facility
Kaylee Baker
April 2023

## Slide 2: 01. Background 02. Problem statement 03. literature review 04. approach 05. proximity to neighbours 06. blast effect mitigation and monitoring 07. Decontamination blasting 08. completion of site work

## Slide 3: Background
History of Initiating Systems
  Safety fuse – 1831
  Electric bridge wire blasting cap – 1832
  Plain detonator – 1864
  Electric detonator – 1870
  Delay electric detonator – 1895
  Detonating cord – 1902
  Igniter cord – 1957
  Shock tube – 1980
  Electronic detonators – 1970s
Early electronics manufacturing facility
Manufacture SmartDet Electronic Detonators 1993 to 2011
Decommissioned to allow for newer technology

## Slide 4: Problem Statement
Inside of building was decontaminated
A drain was situated outside of the building linked to a French drain to cater for non-hazardous effluent
During a risk assessment, the possibility of lead styphnate contamination of the French drain was raised
Extent of contamination not known
Extrapolation of the probability showed that the area could be contaminated with up to 40kg
Soda Ash used periodically during operations to assist with desensitization

## Slide 5: Approach
GPR (2012)
Remote Drilling
Involvement of legislators
Decontamination Options
Chemical Neutralisation
Digging
Soda Ash
Blasting

## Slide 6: Proximity to Neighbours

## Slide 7: Blast effect mitigation and monitoring
Experts were consulted
  Exclusion zone of 210m determined
Tenants evacuated the area when blasting took place
  Drones used to monitor surrounding area for activity
  Security monitoring area
Blasting done during school holidays
Dogs moved to SPCA during the week of the blasting
Blast barricade erected to protect nearby buildings
Sand bags used to minimise flyrock and assist with containing blast
Four NOMIS Seismographs
  Position 1 – 1,090 m – Shell garage
  Position 2 – 445 m – Pinelands business park gate
  Position 3 – 130 m – Contractor facility
  Position 4 – 352 m – Founders Hill College
Notes:   Ground cratering
  Ejection of soil lumps and other missiles over a large area
  Propagation of a blast wave, exerting dynamic pressure forces on structures
  High intensity (i.e. high dB-level) sound waves

## Slide 8: Decontamination blasting
  Explosive charge – 5kg per blast
Total of 18 shots – approximately 90kg
3 craters formed
Drone footage of blasting taken
Drain area was also blasted
No evidence of a French drain could be found
Layer of white powder found in the ground
  Four NOMIS Seismographs
  Position 1: Max 123.2 dB
  Position 2: Max 128.7 dB
  Position 3: Max 148.1 dB
  Position 4: Max 136.3 dB
Notes: 134 USBM threshold for possible cosmetic damage to residences*
All blasts registered an air blast reading at station 3 that exceeded the USBM recommended maximum level for prevention of human irritation (this area was evacuated prior to blasting). Four blasts registered an air blast reading at station 4 that exceeded the USBM recommended maximum level for prevention of human irritation. No blasts registered an air blast reading at stations 1 and 2 that exceeded the USBM recommended maximum level for prevention of human irritation.

## Slide 9: Drone footage

## Slide 10: Completion of site work
  Building refurbished
  Earmarked for Schedule III non-explosive store

## Slide 11: Thank you