## Sheet1
GPG's and Database
GPG | Lead | Team Members (Pledges for assistance) | Progress
Explosives Security | Noel Hsu | 25 participants. | Participants are contributing content to the GPG. Work will continue into 2025.
Explosives Transport | Noel Hsu | Ken Price(Individual Associate),Edward Felix(AECI), Nadia Engler(Austin),Brian Deveraj (Expert Panel) , Mark Moats (Dyno) | On hold pending completion of Security GPG. First workshop was held in Salzburg. A working draft was put together by the working group. This will be developed virtually over the coming months.
ANE Transport | Noel Hsu | Ken Price (Expert Panel) | Complete
Shocktube | John Jones | Ronald Huggins(AECI),Lenka Mikulencakova (Austin Powder),Jan Jidestig (Austin Powder) , Fran Jansen ( Dyno) | One GPG completed through the draft stage and first round of review. The Feburary meeting had low attendance due to travel schedules. Seven more GPGs have been assigned, and one more uploaded for draft review, next meeting scheduled in May.
Primaries | Ralf Weber | Ralf Weber(Austin),Christo Peltz(AECI), Tony Rowe(Consultant), Wen Yu(Expert Panel), Roman Vala (Austin Powder),Jan Jidestig (Austin Powder) | GPG to be issued, but othe PE's to be covered in the next review. An idustry wide discussion group was initiated to highlight safety opportunites for sharing and learning in the primaries product lifecycle.
ESD | Dan Reinke/Heather Reid | Technical steering group volunteers identified in session at Congress and first meeting held 12 June to review ESD e-learning materials. | Complete- ESD Module posted on eLearning Portal
Management of Change | Thierry Rousse/Bob Woolley | Bob Woolley, Thierry Rousse, Joao Roorda, Nadia Engler, Diana Lazarte, Paulo Siqueira, Joanne Della-Rovere, Marion Harouard, Dawn Goosen. | The MOC Working Group have been working to identify as provider for the MOC eLearning package. After assessing three proposals, a decision has been made to work with video creation company Proxymité. The next step is for the WG to finalise the scripts and incident summaries that will be included in the training package.
Process Safety Incidents | Neil Franklin/Christo Peltz | Neil Franklin (AECI), Wen Yu (Expert Panel) , Greg Walker (Dyno), Scott Pelling (Orica), Johanne Della Rovere (EPC), Riha Faleh (EPC) | No comments received from the identified review team since the last meeting. Ridha Faleh (EPC) has replaced Thierry Rousse on this working group. The GPG is to be revieved by: Martin Held, Stephenie de Nichilo, Nadia Engler,Noel Hsu,Heather Reid.
Basis of Safety | Paulo Siquera/Ludo Turlin | Andy Begg,Paulo Siquera/Ludo Turlin | The module has basically been completed and has been available to members for several weeks. There are still sections to be populated and existing sections to be updated as new files become available. The further development of this module is now almost entirely down to members to provide files.
ENEAX eLearning Module | Martin Held/Andy Begg |  | Complete
Argyle Incident | Liaison with Orica Initiative :Martin Held | Martin Held(Austin Powder), Andy Begg(Individual Associate),James Bonnor(Orica),Peter Skinner( Orica) | Orica is in the process of developing an eLearning module with animation for internal training , but are prepared to give SAFEX access to the final product. Information exchang between the parties will be ongoing. Waiting for update.
Porgera Incident | Stephenie de Nichilo | Michael Jennings (Dyno), Greg Walker (Dyno), Jen Oetting (Dyno) | The video if the incident was presented at the SAFEX Board meeting in January. Waiting on Dyno for final version to go on the SAFEX website.
Safety Management System | Andy Begg | To be decided | The structure has been decided and will be loaded onto the website shortly. An introduction to the system is given n the article in this copy of the Newsletter.